## NCS-04WFB 10k
NCS-04WFB 1.5K ship before by end of Dec. 2018 from Safewell
| Descripition | Expected Finish Date | Status | Finish date
1 | NO to confirm the BOM | 2018-10-12 | Done | 2018-10-12
2 | NO to confirm function NCS-04WFB sample | 2018-10-24 | Done | 2018-10-24
3 | Safwell to get electronic part files and instruction | 2018-10-26 | Done | 2018-10-29
4 | NO to confirm dieline for color box | 2018-10-29
5 | Safewell to get 1.5k PO | 2018-10-30
6 | Safewell to get confirmation for construction of antenna | 2018-10-31
7 | Safwell to start tooling for plastic part, antenna | 2018-10-31
8 | NO to provide documents for color box artwork, stickers, QSG | 2018-11-05
9 | Safewell to finish development of electronic parts | 2018-11-20
10 | Safewell to provide color box, sticker samples for approval | 2018-11-20
11 | NO to provide F/W for GOLDEN SAMPLES | 2018-11-20
12 | Safewell to provide GOLDEN sample | 2018-11-20
13 | Safewell to finish DOJ testing | 2018-11-20
14 | Safewell to finish FCC testing | 2018-11-20
15 | Safewell to start mass prodcution | 2018-11-21
16 | Safewell to finish all toolings inculed keypad,indicator board, plastic part and antenna | 2018-11-30
17 | NO to test and confirm GOLDEN sample | 2018-12-04
18 | Safewell to assemble completed safe | 2018-12-20
19 | Safewell to finsih completed safe | 2018-12-25
20 | NO to finish inspection completed safe | 2018-12-27
21 | 1.5K ready for loading | 2018-12-28

## 细化日程
04款 WIFI模组不可拆卸案 生产计划：
2018年
| 11月 | [29 empty] | 12月
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
电子与FW
电路初版确定
FW初版确定
生产物料确定
100个试产 物料采购(包括wifi模组)
物料确认
电子件生产，测试和工具交接
100个电路板试产
生产Strandar Operaition Process文档作成
试产问题点，产品改善，生产改善
试产结果判定会议，通过即可以量产，不通过不可量产
1.4K电子件尚缺物料准备，量产
机构 | 11月 1: 机构设计确定(包括天线)
20套3D打印塑胶件 验证和修改
生产物料确定
开模和模具品物料采购
20套其他物料采购，如面壳，按键，排线，EVM等
整箱生产，测试和工具交接，包括label打印
20个箱子试产(尽量使用模具品，如赶不上可使用3D打印塑料件)
生产Strandar Operaition Process文档作成
试产问题点，产品改善，生产改善
试产结果判定会议，通过即可以量产，不通过不可量产
黄金样品和验收标准确定，PAS等
正式开始1.5K 量产
辅材与认证 | 11月 1: 外箱，包装，说明书，附件，FCC，DOJ等。